## Feature Tracker
OrgSight ¦ Feature Development Tracker
Generated: 16 Jun 2026 ¦ Features 1–6: Completed ¦ Features 7–11: Pending ¦ Source: OrgSight Detailed Functionality_DTS
# | Category | Feature / Change Request | Description | Reference (DTS) | Status | Complexity | What Was Built | Remarks / Feedback | Owner | Target Date | Last Updated
▌ CORE MODELING
1 | Core Modeling | Org Modeling (Add / Close / Change / Clone Positions) | Build a future-state org chart off the baseline in a draft. Actions are colour-coded and the as-is remains untouched. Includes add, close, change, and clone position operations. | Modeling 37:39–57:45 | Completed | High | Full draft-mode modeling engine implemented. Position-level CRUD operations with colour-coded diff overlay on the org chart.
2 | Core Modeling | Rate-Card Costing | Property combination (location + dept + grade) maps to indicative cost, auto-applied to new/changed positions. Quartile options and per-position manual override using existing FLC data. | Modeling 21:34–26:45 | Completed | High | Rate-card lookup by location/dept/grade implemented. Quartile selector and manual override per position working. FLC data integrated.
3 | Core Modeling | Changes Report + Baseline vs To-Be View | Size/cost delta (baseline / to-be / net) by any dimension, plus a side-by-side before/after comparison. This is the core client deliverable from any modeling exercise. | Modeling 1:01:42, 1:12:17 | Completed | Medium | Delta report by dimension (headcount, cost) built. Side-by-side baseline vs to-be view rendered. Export to CSV/Excel supported.
4 | Core Modeling | Activity Analysis (People → Roles → Activities → Savings) | Map activities to roles, apply automation/AI/stop/BPO levers with dates, and report FTE & cost impact over time. Aligns with AVA; per-person override capability. | Activity 11:50–49:50 | Completed | High | Activity-to-role mapping with lever assignment (Automate / AI / Stop / BPO) built. FTE & cost savings timeline chart generated. Per-person override supported.
5 | Core Modeling | Action Dates + Phasing View | Attach an effective date to each modeled change to show headcount removals/adds by month and compare full-year vs run-rate cost. | Modeling 1:05:30 | Completed | Medium | Effective date field added to each change action. Monthly phasing waterfall and full-year vs run-rate cost comparison implemented.
6 | Core Modeling | Validate the To-Be State | Flag modeling mistakes on the future state — e.g. closed manager with open reports, change with no reason code. Mirrors the existing Validate module but applied to drafts. | Modeling 40:39 | Completed | Medium | Future-state validation rules implemented: orphaned reports, missing reason codes, span violations. Warnings surfaced in the draft before publishing.
▌ DEEPEN EXISTING
7 | Deepen Existing | Calculated Properties (Formula Columns) | Let users define a computed column off existing properties, e.g. cost-per-report, span ratio. Closes the Excel gap without needing a full Gizmo-style expression engine. | Deck (Expressions) | Completed | Medium | Right now : a Formula Editor panel in the workspace where you can write simple math expressions referencing any column in your dataset: Cost per FTE = FLC / FTE Annual Cost = Monthly_Salary * 12 Total Comp = Base_Salary + Bonus + Benefits Cost Ratio = FLC / Total_Budget * 100 Supports: +, -, *, /, parentheses, and numeric literals. As you type the expression, a live preview evaluates it against the first record so you can see the result instantly. If the expression is invalid (e.g., references a column that doesn't exist), you see a red error message inline. | Define the scope - to expand or not? (IF conditional logic)
8 | Deepen Existing | Properties Cleaning Heatmap | Heatmap of missing values across critical fields, complementing existing Validate / Filter Errors modules. Highlights data quality gaps at a glance. | Deck (data validation) | Completed | Low |  | Can reuse Validate module data; primarily a UI/visualisation addition.
9 | Deepen Existing | Target-Span Alignment + Micro-Team Detection | Identify managers above/below a target span, quantify the FTE opportunity, and detect 1:1 / thin-layer structures. Extends the Spans & Layers module. | Modeling 1:22:52 | Completed | Medium |  | Builds on S&L module. Needs configurable target-span input and FTE delta calc.
▌ BEYOND ORGVUE
10 | Beyond OrgVue | Change-Impact Warnings (Leapfrog Detection) | Auto-flag on the future state: too few managers, geography gaps, tenure skew. Proactive risk signals not currently in OrgVue. | Modeling 1:18:53 | Pending | Medium |  | Differentiating feature vs OrgVue. Define warning thresholds as config.
11 | Beyond OrgVue | Editable-After-Kickoff Modeling Config | Allow modeling configuration (including rate card) to be changed after a modeling exercise has already started — fixing a known OrgVue limitation. | Modeling 30:57 | Pending | Low |  | Requires versioning/re-apply logic for config changes mid-exercise.

## Summary Dashboard
OrgSight ¦ Summary Dashboard
As of 16 Jun 2026
Total Features | Completed | Pending | High Complexity | Medium Complexity | Low Complexity
11 | 6 | 5 | 2 | 7 | 2
# | Feature | Category | Status | Complexity | Reference
1 | Org Modeling (Add / Close / Change / Clone Positions) | Core Modeling | Completed | High | Modeling 37:39–57:45
2 | Rate-Card Costing | Core Modeling | Completed | High | Modeling 21:34–26:45
3 | Changes Report + Baseline vs To-Be View | Core Modeling | Completed | Medium | Modeling 1:01:42, 1:12:17
4 | Activity Analysis (People → Roles → Activities → Savings) | Core Modeling | Completed | High | Activity 11:50–49:50
5 | Action Dates + Phasing View | Core Modeling | Completed | Medium | Modeling 1:05:30
6 | Validate the To-Be State | Core Modeling | Completed | Medium | Modeling 40:39
7 | Calculated Properties (Formula Columns) | Deepen Existing | Completed | Medium | Deck (Expressions)
8 | Properties Cleaning Heatmap | Deepen Existing | Completed | Low | Deck (data validation)
9 | Target-Span Alignment + Micro-Team Detection | Deepen Existing | Pending | Medium | Modeling 1:22:52
10 | Change-Impact Warnings (Leapfrog Detection) | Beyond OrgVue | Pending | Medium | Modeling 1:18:53
11 | Editable-After-Kickoff Modeling Config | Beyond OrgVue | Pending | Low | Modeling 30:57